# Agency Overview

The NYC Police Department's (NYPD) mission is to protect the lives and property of City residents and help to ensure enforcement of the laws. The NYPD meets its objectives by responding to emergency calls, particularly crimes in progress, conducting ongoing investigations into criminal activity, apprehending violators and addressing legal issues which affect the quality of life in the city. The NYPD is divided into 76 precincts and currently occupies 275 facilities, 113 of which are city-owned, 116 locations are being leased or authorized by Permit Agreement, and 46 are owned by the Housing or Transit Authority. Additionally, the Department also owns and/or maintains several administrative, training, repair and storage facilities.

# Current Budget Summary

The January 2008 Capital Commitment Plan includes $1.58 billion (City funds only) in Fiscals 2008-2011 for the Police Department. This represents 3 percent of the City’s total $52.5 billion January Plan for Fiscals 2008-2011. The agency's January Commitment Plan for Fiscals 2008-2011 is 2 percent greater than the $1.55 billion in the September Commitment Plan, an increase of $30 million.

Over the past five years, the NYPD has only committed an average of 33 percent of its annual capital plan. Therefore, it is assumed that a large portion of the NYPD’s Fiscal 2008 capital plan will be rolled into Fiscal 2009, thus greatly increasing the size of the Fiscals 2009-2012 capital plan. Since Adoption last June, the Capital Commitment Plan for Fiscal 2008 has decreased from $365 million to $341 million, a reduction of $24 million or 7 percent.

Current NYPD appropriations total $495 million in City funds for Fiscal 2008. These appropriations are to be used to finance the Department’s $303 million City-funded Fiscal 2008 capital commitment program. The agency has 63 percent more funding than it needs to meet its entire capital commitment program for the current fiscal year.

The Police Department's capital commitments for the last five years are shown below:

| FIVE YEAR HISTORY – CAPITAL BUDGET ($ in millions) |
| --- |
|  | FY03 | FY04 | FY05 | FY06 | FY07 |
| CITY | 81 | 65 | 43 | 77 | 90 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 81 | 65 | 43 | 77 | 90 |

The Adopted Four-Year Capital Plan is shown below:

| ADOPTED CAPITAL BUDGET – SEPTEMBER 2007 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 365.0 | 1,012.7 | 90.3 | 82.0 | 1,549.7 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 365.0 | 1,012.7 | 90.3 | 82.0 | 1,549.7 |

The Preliminary Four-Year Capital Plan is shown below:

| PRELIMINARY CAPITAL PLAN – JANUARY 2008 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 340.6 | 1,074.0 | 90.0 | 78.3 | 1,582.9 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 340.6 | 1,074.0 | 90.0 | 78.3 | 1,582.9 |

# PRELIMINARY BUDGET HIGHLIGHTS:

Planned Commitments for Fiscal 2008 through Fiscal 2011

In the January Capital Plan, the Department’s planned commitments for Fiscals 2008-2011 are $1.58 billion.  The Department’s planned commitments increased by $30 million or 2 percent since the September Capital Plan.  Significant changes to the NYPD’s January Plan for Fiscals 2008-2011 that attributed to the net increase in funding include:

- An increase of $50.2 million for new computer equipment for the Department including $28 million for a new property evidence tracking system.

- An additional $32 million for a new MTA Radio project which will enhance tunnel communication capability.

- A decrease of $45 million for the Central Park Precinct due to a deregistered contract.  The funding is expected to be restored in the Executive Budget and plans for the project to be completed remain unchanged.

NYPD planned commitments in the January Capital Plan for Fiscals 2008-2011 include:

- $1 billion for a new Police Academy – The NYPD plans to build a new Police Academy at a 30-acre site in College Point, Queens that currently houses an NYPD Tow Pound.  This will replace the existing outdated Academy in the Gramercy section of Manhattan and will consolidate the Department’s training programs to one location.  The new Academy will feature; instruction space, support and administration buildings, a field house, indoor shooting ranges, a tactical village, housing facility, driver training fields, K-9 environment, parking, vehicle maintenance facility and a utility plant.  This project is in the design stage and the City plans to break ground before the end of 2009.

- $151 million for the acquisition and installation of computer equipment including; $28 million for the aforementioned Property Evidence Tracking System, $10.4 million for the NYPD Real Time Crime Center, $15.5 million for a mainframe CPU, $15 million for the Lower Manhattan Security Initiative, $17.2 million for a LAN/WAN network upgrade, and $13 million for a Parking Ticket Device System.

- Approximately $120 million is planned for construction of a new Staten Island Precinct and new buildings for the 40th (Bronx), 66th  (Brooklyn), 70th   (Brooklyn), 110th (Queens), 120th (Staten Island) and 121st (Staten Island) Precincts.

Agency Overview

The City is responsible for the construction and maintenance of court facilities within its boundaries. New York City currently has 21 court facilities, which are maintained by the Department of Citywide Administrative Services (DCAS). Chapter 825 of the State Laws of 1987 mandates the City to assess the current court facility conditions, to anticipate future needs, and to submit a capital plan to the State Office of Court Administration. After completing a comprehensive review of New York City’s court requirements, the City has embarked upon a $2 billion court renovation and construction program that has been approved by the State Office of Court Administration. Under the plan, the Dormitory Authority of the State of New York (DASNY) will issue bonds to finance the $2 billion plan and will assume construction management responsibility, along with DCAS, the Department of Design and Construction (DDC), and the Economic Development Corporation (EDC), or, in some cases, private developers, on a project-by-project basis. The City will fund all debt service costs relating to DASNY's debt issuance for court construction and reconstruction projects.

# Current Budget Summary

The January 2008 Capital Commitment Plan includes $1.213 billion in Fiscals 2008-2011 for the Courts Program (including City and non-City funds). This represents 2.3 percent of the City’s total $52.5 billion January Plan for Fiscals 2008-2011. The program's January Commitment Plan for Fiscals 2008-2011 is one percent greater than the $1.2 billion in the September Commitment Plan, an increase of $ 13 million

Over the past five years, an average of 19 percent of the Courts Program is committed annually. Therefore, it is assumed that a large portion of the program’s Fiscal 2008 capital plan will be rolled into Fiscal 2009, thus greatly increasing the size of the Fiscals 2009-2012 capital plan. Since adoption last June, the Capital Commitment Plan for Fiscal 2008 has fallen from $255 million to $239 million, a decrease of $16 million or 6 percent.

Current Courts Program appropriations total $1.4 billion in City funds for Fiscal 2008. These appropriations are to be used to finance the Department’s $235 million City-funded Fiscal 2008 capital program. The agency has five times more funding than it needs to meet its entire capital commitment program for the current fiscal year.

The Courts Program’s capital commitments for the last five years are shown below:

| FIVE YEAR HISTORY – CAPITAL BUDGET ($ in millions) |
| --- |
|  | FY03 | FY04 | FY05 | FY06 | FY07 |
| CITY | 86 | 73 | 119 | 142 | 161 |
| NON-CITY | 10 | 2 | 3 | -21 | 0 |
| TOTAL | 96 | 75 | 122 | 121 | 161 |

The Adopted Four-Year Capital Plan is shown below:

| ADOPTED CAPITAL BUDGET – SEPTEMBER 2007 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 254.7 | 883.3 | 10.9 | 51.5 | 1,200.4 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 254.7 | 883.3 | 10.9 | 51.5 | 1,200.4 |

The Preliminary Four-Year Capital Plan is shown below:

| PRELIMINARY CAPITAL PLAN – JANUARY 2008 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 239.4 | 901.8 | 27.9 | 44.0 | 1,213.1 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 239.4 | 901.8 | 27.9 | 44.0 | 1,213.1 |

# PRELIMINARY BUDGET HIGHLIGHTS:

Planned Commitments for Fiscals 2008-2011

The Court’s Program’s planned commitments for Fiscals 2008-2011 increased from $1.200 billion to $1.213 billion or one percent, in the January Plan.  The increase in the planned commitments is the net result of relatively small adjustments to various projects.

Highlights of larger projects in the Court’s Program in the January Capital Plan include:

- $628 million for the new Brooklyn Court facility at 330 Jay Street.

- $200 million for the new Staten Island Family and Criminal Court.

- $77 million for the Bronx Court facility at 215 East 161st Street

- $57 million for the Bronx Court facility at 851 Grand Concourse.

- $45 million for the Brooklyn Court Facilities at 120 Schermerhorn Street.

- $30 million for the Manhattan Court facility at 100 Centre Street

- $25 million for the Manhattan Court facility at 60 Lafayette Street

- $24 million for the Manhattan Court facility at 60 Centre Street.

- $15 million for the Queens Court facility at 88-11 Sutphin Blvd.

- $15 million for the Manhattan Community Court facility at 315 West 54th Street.

## Agency Overview

The Department of Juvenile Justice (DJJ) operates secure detention facilities in the Bronx and Brooklyn; provides non-secure detention services at agency-operated and contractual group homes; transports detainees from detention facilities to the Family, Criminal, and Supreme Courts; supervises detainees held in the Family Court detention rooms; and provides community-based preventive and aftercare services.

The three secure facilities are: Bridges Juvenile Center (formerly known as Spofford), located in the Bronx, which handles the intake of juveniles into the system; Horizons Juvenile Center, also located in the Bronx, which serves juvenile detainees from the Bronx and Manhattan; and Crossroads Juvenile Center, located in Brooklyn, serving juvenile detainees from Queens, Brooklyn, and Staten Island.

# Current Budget Summary

The January 2008 Capital Commitment Plan includes $14.9 million in Fiscals 2008-2011 for the Department of Juvenile Justice (all City funds). This represents less than one percent of the City’s total $52.5 billion January Plan for Fiscals 2008-2011. The program's January Commitment Plan for Fiscals 2008-2011 is $100,000 more than the $14.8 million in the September Commitment Plan.

Over the past five years, DJJ has only committed an average of 19 percent of its annual capital plan. Therefore, it is assumed that a large portion of the program’s Fiscal 2008 capital plan will be rolled into Fiscal 2009, thus greatly increasing the size of the Fiscals 2009-2012 capital plan. Since Adoption last June, the Capital Commitment Plan for Fiscal 2008 has decreased from $8.1 million to $5.1 million, a reduction of $3 million or 37 percent.

Current DJJ appropriations total $16.7 million in City funds for Fiscal 2008. These appropriations are to be used to finance the Department’s $4.1 million City-funded Fiscal 2008 capital commitment program. The agency has over three times more funding than it needs to meet its entire capital commitment program for the current fiscal year.

The Department of Juvenile Justice’s capital commitments for the last five years are shown below:

| FIVE YEAR HISTORY – CAPITAL BUDGET ($ in millions) |
| --- |
|  | FY03 | FY04 | FY05 | FY06 | FY07 |
| CITY | -1 | 1 | 5 | 2 | 3 |
| NON-CITY | -1 | 0 | 0 | 0 | 0 |
| TOTAL | -2 | 1 | 5 | 2 | 3 |

The Adopted Four-Year Capital Plan is shown below:

| ADOPTED CAPITAL BUDGET – SEPTEMBER 2007 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 8.1 | 1.7 | 1.3 | 3.7 | 14.8 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 8.1 | 1.7 | 1.3 | 3.7 | 14.8 |

The Preliminary Four-Year Capital Plan is shown below:

| PRELIMINARY CAPITAL PLAN – JANUARY 2008 ($ in millions) |
| --- |
|  | FY08 | FY09 | FY10 | FY11 | FY’s 08-11 |
| CITY | 5.1 | 4.8 | 1.3 | 3.7 | 14.9 |
| NON-CITY | 0 | 0 | 0 | 0 | 0 |
| TOTAL | 5.1 | 4.8 | 1.3 | 3.7 | 14.9 |

PRELIMINARY BUDGET HIGHLIGHTS:

### Planned Commitments for Fiscal 2008 through Fiscal 2011

The January Capital Plan includes a total of $15 million for the DJJ for Fiscals 2008-2011.  This same amount the Agency had in its September Plan.  Planned commitments for Fiscal 2008 decreased by $3 million which is being pushed into Fiscal 2009.

Of the $15 million total planned commitments for Fiscals 2008-2011; $13.3 million is allocated for renovation and improvements to DJJ’s secure detention facilities: the Bridges (formerly Spofford), Horizons, and Crossroads Juvenile Centers; $1.4 million for the build out of new central offices; $160,000 to replace secure passenger vehicles; and $213,000 for renovations and improvements to agency operated non-secure detention facilities.